## Sheet1
¦RoundRobin | Condition 1 | Condition 2 | WebFormName | TableName |  | ScriptName
N | N | N | WF_RRN_OneN_TwoN | WF_RRN_OneN_TwoN_Test | TC013 | TC013_WF_RRN_OneN_TwoN
N | N | YN | WF_RRN_OneN_TwoYN | WF_RRN_OneN_TwoYN_Test | TC014 | TC014_WF_RRN_OneN_TwoYN
N | N | Y | WF_RRN_OneN_TwoY | WF_RRN_OneN_TwoY_Test | TC015 | TC015_WF_RRN_OneN_TwoY
N | Y | N | WF_RRN_OneY_TwoN | WF_RRN_OneY_TwoN_Test | TC016 | TC016_WF_RRN_OneY_TwoN
N | Y | YN | WF_RRN_OneY_TwoYN | WF_RRN_OneY_TwoYN_Test | TC017 | TC017_WF_RRN_OneY_TwoYN
N | Y | Y | WF_RRN_OneY_TwoY | WF_RRN_OneY_TwoY_Test | TC018 | TC018_WF_RRN_OneY_TwoY
N | YN | N | WF_RRN_OneYN_TwoN | WF_RRN_OneYN_TwoN_Test | TC019 | TC019_WF_RRN_OneYN_TwoN
N | YN | YN | WF_RRN_OneYN_TwoYN | WF_RRN_OneYN_TwoYN_Test | TC020 | TC020_WF_RRN_OneYN_TwoYN
N | YN | Y | WF_RRN_OneYN_TwoY | WF_RRN_OneYN_TwoY_Test | TC021 | TC021_WF_RRN_OneYN_TwoY
Y | N | N | WF_RRY_OneN_TwoN | WF_RRY_OneN_TwoN_Test | TC022 | TC022_WF_RRY_OneN_TwoN
Y | N | YN | WF_RRY_OneN_TwoYN | WF_RRY_OneN_TwoYN_Test | TC023 | TC023_WF_RRY_OneN_TwoYN
Y | N | Y | WF_RRY_OneN_TwoY | WF_RRY_OneN_TwoY_Test | TC024 | TC024_WF_RRY_OneN_TwoY
Y | Y | N | WF_RRY_OneY_TwoN | WF_RRY_OneY_TwoN_Test | TC025 | TC025_WF_RRY_OneY_TwoN
Y | Y | YN | WF_RRY_OneY_TwoYN | WF_RRY_OneY_TwoYN_Test | TC026 | TC026_WF_RRY_OneY_TwoYN
Y | Y | Y | WF_RRY_OneY_TwoY | WF_RRY_OneY_TwoY_Test | TC027 | TC027_WF_RRY_OneY_TwoY
Y | YN | N | WF_RRY_OneYN_TwoN | WF_RRY_OneYN_TwoN_Test | TC028 | TC028_WF_RRY_OneYN_TwoN
Y | YN | YN | WF_RRY_OneYN_TwoYN | WF_RRY_OneYN_TwoYN_Test | TC029 | TC029_WF_RRY_OneYN_TwoYN
Y | YN | Y | WF_RRY_OneYN_TwoY | WF_RRY_OneYN_TwoY_Test | TC030 | TC030_WF_RRY_OneYN_TwoY
YN | N | N | WF_RRYN_OneN_TwoN | WF_RRYN_OneN_TwoN_Test | TC031 | TC031_WF_RRYN_OneN_TwoN
YN | N | YN | WF_RRYN_OneN_TwoYN | WF_RRYN_OneN_TwoYN_Test | TC032 | TC032_WF_RRYN_OneN_TwoYN
YN | N | Y | WF_RRYN_OneN_TwoY | WF_RRYN_OneN_TwoY_Test | TC033 | TC033_WF_RRYN_OneN_TwoY
YN | Y | N | WF_RRYN_OneY_TwoN | WF_RRYN_OneY_TwoN_Test | TC034 | TC034_WF_RRYN_OneY_TwoN
YN | Y | YN | WF_RRYN_OneY_TwoYN | WF_RRYN_OneY_TwoYN_Test | TC035 | TC035_WF_RRYN_OneY_TwoYN
YN | Y | Y | WF_RRYN_OneY_TwoY | WF_RRYN_OneY_TwoY_Test | TC036 | TC036_WF_RRYN_OneY_TwoY
YN | YN | N | WF_RRYN_OneYN_TwoN | WF_RRYN_OneYN_TwoN_Test | TC037 | TC037_WF_RRYN_OneYN_TwoN
YN | YN | YN | WF_RRYN_OneYN_TwoYN | WF_RRYN_OneYN_TwoYN_Test | TC038 | TC038_WF_RRYN_OneYN_TwoYN
YN | YN | Y | WF_RRYN_OneYN_TwoY | WF_RRYN_OneYN_TwoY_Test | TC039 | TC039_WF_RRYN_OneYN_TwoY

## Dry Run
Script Name | Data Table Name | Status | WebFormName
TC001_WF_RRUserY_NoCondition | WF_RRUserY_NoCondition_Test | Pass | WF_RRUserY_NoCondition | Yes
TC002_WF_RRUserYN_NoCondition | WF_RRUserYN_NoCondition_Test | Pass | WF_RRUserYN_NoCondition | Yes
TC003_WF_RRUserN_NoCondition | WF_RRUserN_NoCondition_Test | Pass | WF_RRUserN_NoCondition | Yes
TC004_WF_RRUserY_OneConditionY | WF_RRUserY_OneConditionY_Test | Pass | WF_RRUserY_OneConditionY | Yes
TC005_WF_RRUserYN_OneConditionYN | WF_RRUserYN_OneConditionYN_Test | Pass | WF_RRUserYN_OneConditionYN | Yes
TC006_WF_RRUserN_OneConditionY | WF_RRUserN_OneConditionY_Test | Pass | WF_RRUserN_OneConditionY | Yes
TC007_WF_RRUserY_OneConditionN | WF_RRUserY_OneConditionN_Test | Pass | WF_RRUserY_OneConditionN | Yes
TC008_WF_RRUserY_OneConditionYN | WF_RRUserY_OneConditionYN_Test | Pass | WF_RRUserY_OneConditionYN | Done
TC009_WF_RRUserN_OneConditionYN | WF_RRUserN_OneConditionYN_Test | Pass | WF_RRUserN_OneConditionYN | Done
TC010_WF_RRUserYN_OneConditionY | WF_RRUserYN_OneConditionY_Test | Pass | WF_RRUserYN_OneConditionY | 2024-06-22 | OneCondition | RRUser | Status
TC011_WF_RRUserN_OneConditionN | WF_RRUserN_OneConditionN_Test | Done | WF_RRUserN_OneConditionN | Done | Y | Y | Done
TC012_WF_RRUserYN_OneConditionN | WF_RRUserYN_OneConditionN_Test |  | WF_RRUserYN_OneConditionN | Done | YN | YN | Done
[5 empty] | N | Y | Done
[5 empty] | Y | N | Done
[5 empty] | YN | Y | Not Started
[5 empty] | YN | N | Not Started
[5 empty] | Y | YN | Not Started
[5 empty] | N | N | Not Started
[5 empty] | N | YN | Not Started

## Sheet2
ScriptName | DataSheet | WebForm | Script | Dry Run | Comments
TC013_WF_RRN_OneN_TwoN | Done | Done | Done | Done | Record Not Created. Dry run completed successfully.
TC014_WF_RRN_OneN_TwoYN | Done | Done | Done | Done | Cond 2 value Tamilnadu selected,but users are not assigning based on Y/N. It is assigning as all Yes in Cond2 users list | Informed to Gopal
TC015_WF_RRN_OneN_TwoY | Done | Done | Done | Done | Pass
TC016_WF_RRN_OneY_TwoN | Done | Done | Done | Done | Pass
TC017_WF_RRN_OneY_TwoYN | Done | Done | Done | Done | Known Issue at TC014
TC018_WF_RRN_OneY_TwoY | Done | Done | Done | Done
TC019_WF_RRN_OneYN_TwoN | Done | Done | Done | Done | (Multicombo)Condition 1 value "one" selected. But users are not assigned alternatively as configured. It is assigning one by one. Condition 2 value is configured with all Availability No user, but if the condition value matches, it each user one by one | Same as Known Issue at TC014
TC020_WF_RRN_OneYN_TwoYN | Done | Done | Done | Done | (Multicombo)Condition 1 value "one" selected. But users are not assigned alternatively as configured. It is assigning one by one. (Picklist)Condition 2 value tamilnadu" selected. But users are not assigned alternatively as configured. It is assigning one by one. | Same as Known Issue at TC014
TC021_WF_RRN_OneYN_TwoY | Done | Done | Done | Done | Issue on Condition 1 Y/N | Same as Known Issue at TC014
TC022_WF_RRY_OneN_TwoN | Done | Done | Done | Done | Issue on Condition 1 and Condition 2.(One N and Two N) | Same as Known Issue at TC014 | 2024-06-26
TC023_WF_RRY_OneN_TwoYN | Done | Done | Done | Done | Only when condition 1 and condition 2 matches, condition 1 will look for user assignment from Round Robin Users list. Only if condition matches, and it's users are YN. It fetches it by one by one as all are Y. | Same as Known Issue at TC014 | 2024-06-26
TC024_WF_RRY_OneN_TwoY |  |  |  |  | If condition 1 matches , though userslist are N, it fetches condition1 users one by one. |  | 2024-06-26
TC025_WF_RRY_OneY_TwoN | Done | Done | Done | Done | No Issues |  | 2024-06-26
TC026_WF_RRY_OneY_TwoYN | Done | Done | Done | Done | Issue: If Condition 2 matches, it fetches users one by one for Y and N availability. | Same as Known Issue at TC014
TC027_WF_RRY_OneY_TwoY | Done | Done | Done | Done
TC028_WF_RRY_OneYN_TwoN | Done | Done | Done | Done | Issue: Condition 1 Matches and considers YN as all Yes. | Same as Known Issue at TC014 | 2024-06-27
TC029_WF_RRY_OneYN_TwoYN | Done | Done | Done | Done | Condition 1 and Condition 1 fails as it considers all the users as Available instead of YN. | Same as Known Issue at TC014 | 2024-06-27
TC030_WF_RRY_OneYN_TwoY | Done | Done | Done | Done | Condition 1 considers all the users as Available instead of YN. | Same as Known Issue at TC014 | 2024-06-27
TC031_WF_RRYN_OneN_TwoN | Done | Done | Done | Done | First Time after configuration, users pick from condition 1 or 2 users even though they are not available.Second time, it looks for users in Main Round Robin. | Second Issue. Already Reported by Manual Team. | 2024-06-27
TC032_WF_RRYN_OneN_TwoYN
TC033_WF_RRYN_OneN_TwoY
TC034_WF_RRYN_OneY_TwoN
TC035_WF_RRYN_OneY_TwoYN
TC036_WF_RRYN_OneY_TwoY
TC037_WF_RRYN_OneYN_TwoN
TC038_WF_RRYN_OneYN_TwoYN
TC039_WF_RRYN_OneYN_TwoY

## Sheet5
Scenario | WebForm | DataTable | Script Dev | Dry Run | Date
CRM User Assignment When No Users in Round Robin, No Available Users in Condition 1 and Condition 2 | Done | Done | Done | Done | 2024-06-24
CRM User Assignment When No Users in Round Robin, No Available Users in Condition 1 and Available , UnAvailable Users in Condition 2 | Done | Done | Done | Done
CRM User Assignment When No Users in Round Robin, No Available Users in Condition 1 and Available Users in Condition 2 | Done | Done | Not Started | Not Started
CRM User Assignment When No Users in Round Robin, Available Users in Condition 1 and No Available Users in Condition 2 | Done | Done | Not Started | Not Started
CRM User Assignment When No Users in Round Robin, Available Users in Condition 1 and Available Users in Condition 2 | Done | Done | Not Started | Not Started
CRM User Assignment When No Users in Round Robin, Available & UnAvailable Users in Condition 1 and No Available Users in Condition 2 | Done | Done | Not Started | Not Started

## Sheet3
Round Robin | Condition1 | Condition2 |  | Admin | Availability
No | No | No | Assinged to First | Yes | Yes | fGetFirstAvailableAdminUser
|  |  | Assinged to First | No | Yes | fGetFirstAvailableNonAdminUser
|  |  | Assinged to First | Yes | No | fGetFirstAdminNonAvailabilityUser | first active admin user
|  |  | Assinged to First | No | No | fGetFirstActiveNonAdminUser | first active non admin user
|  |  | Assinged to First | No | No |  | No | Rsoft